| Project name | SAMPLE WORK PLAN |  |
| --- | --- | --- |
| Workplan drafted on: 12/1/2021 |  | Workplan updated on: 1/1/2022 |

| Goal 1 | Improve the health of diabetes patients living in Calhoun County |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | By December 30th 2022, 250 patients with diabetes will participate in diabetes education workshops |  |  |  |  |  |  |  |  |
| Key Activity | Person/Area Responsible | Expected outcome(s) |  |  | Outcome measure(s) | Start date | End Date | Status | Comments |
| Recruit and train workshop leaders and lifestyle coaches who represent the Latino community | Program Director HR Administrator Project Coordinator | 5 Spanish speaking lifestyle coach hired Coaches trained on Living Well with Diabetes and DSME Programs |  |  | Date of position posted and hired Dates of training Post-Training survey results -confidence in materials -satisfaction with training | 1/15/2022 | 4/15/2022 | Not started | Click or tap here to enter text. |
| Organize and host Living Well with Diabetes workshops in accessible community locations | Project Coordinator Coaches | Host 10 Living Well with Diabetes workshops in multiple locations 25 participants enrolled in each Living Well with Diabetes 80% of enrolled participants complete the workshop series |  |  | Dates and location of workshops Number of participants enrolled per workshop Workshop attendance list Percent of participants completing workshops | 4/29/2022 | 12/30/2022 | Not started | Click or tap here to enter text. |
|  |  |  |  | Insert New Activity? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |
|  |  |  | Insert New Objective? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |  |
| Objective | By December 30th, 2022, the project team will publish at least 6 diabetes self-management education articles using culturally specific media. |  |  |  |  |  |  |  |  |
| Key Activity | Person/Area Responsible | Expected outcome(s) |  |  | Outcome measure(s) | Start date | End Date | Status | Comments |
| Identify topics for articles and create a writing calendar | Project Coordinator Coaches | Timeline of articles to be written and published |  |  | Number and list of topics Dates when each article will be worked on and by whom | 4/29/2022 | 11/30/2022 | Not started | Click or tap here to enter text. |
| Publish articles with culturally tailored messages | Project Coordinator Coaches | 1 article published in Latino American Today each month |  |  | Number of articles drafted Number of articles published Topic of articles | 5/1/2022 | 12/30/2022 | Not started | Click or tap here to enter text. |
|  |  |  |  | Insert New Activity? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |
|  |  |  | Insert New Objective? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |  |

| Goal 2 | Reduce rates of prediabetes and provide education on how to prevent diabetes for Calhoun County residents |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Objective | By December 30th, 2022 75% of program participants will see reductions in the level of risk factors to can lead to diabetes and its complications |  |  |  |  |  |  |  |  |
| Key Activity | Person/Area Responsible | Expected outcome(s) |  |  | Outcome measure(s) | Start date | End Date | Status | Comments |
| Implement the National Diabetes Prevention Program tailored to Latino individuals | Project Coordinator Coaches | 10 Latino participants recruited per cycle 80% of participants complete program 16 initial sessions conducted 6 follow-up sessions conducted Pre-post tests administered to all participants and results compiled |  |  | Dates of program Number of participants enrolled Attendance per session Pre-post test statistics -Weight changes -percent achieving target weight -percent achieving fitness target -percent achieving healthy eating goals | 4/29/2022 | 12/30/2022 | Not started | Click or tap here to enter text. |
| Establish a Diabetes Prevention Hotline to provide quick screening and sign-ups for DPP classes | Coaches | Hotline established Hotline reference manual created Flyers posted at local organization |  |  | Number of calls received per month Outcomes of calls | 4/29/2022 | 12/30/2022 | Not started | Click or tap here to enter text. |
|  |  |  |  | Insert New Activity? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |
|  |  |  | Insert New Objective? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |  |
| Objective | By June 30th, 2022 have a Diabetes prevention wellness program established at 2 local large employers in Calhoun County |  |  |  |  |  |  |  |  |
| Key Activity | Person/Area Responsible | Expected outcome(s) |  |  | Outcome measure(s) | Start date | End Date | Status | Comments |
| Identify organizations that are willing to partner on this initiative | Program Director Project Coordinator | Identify 2 employers to pilot the program |  |  | List of Calhoun county employers with at least 100 employees List of potential partners | 1/1/2022 | 6/30/2022 | Not started | Click or tap here to enter text. |
| Incorporate DPP into workplace wellness program | Project Coordinator Coaches | Signed MOU with two participating employers DPP included in each employer’s new employee orientation materials DPP program offerings included in employee handbook 10 employees per employer participates 16 modules of DPP completed per site Post module assessments completed, and results compiled |  |  | Dates of signed MOUs Number of participants per sites Dates and attendance of each module per site Post-assessment statistics -satisfaction with program -Percent of participant who found the information useful | 3/1/2022 | 6/30/2022 | Not started | Click or tap here to enter text. |
|  |  |  |  | Insert New Activity? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |
|  |  |  | Insert New Objective? Click on this cell and then click on the + sign that appears next to it |  |  |  |  |  |  |